## Sheet1
Module / Category | Task Details | Assigned To | Start Date | Due Date | Planned (Hrs) | Actual (Hrs) | Status | End Date | Risk / Comments / Comp Off
| Monthly Team Meeting | Pallavi Singh | 01-Aug-25 | 01-Aug-25 | 2.5 | 2 | Completed
| Email Engagements to Hot deals | Pallavi Singh | 01-Aug-25 | 01-Aug-25 | 1 | 1 | Completed
| BFS Strategy meeting | Pallavi Singh | 01-Aug-25 | 01-Aug-25 | 2 | 2 | Completed
| FreoMoney Operational setup | Pallavi Singh | 01-Aug-25 | 01-Aug-25 | 1.5 | 1 | Completed
| Monthly Team Meeting | Yaser Mohammed | 01-Aug-25 | 01-Aug-25 | 2.5 | 6 | Completed
| BFS Strategy meeting | Yaser Mohammed | 01-Aug-25 | 01-Aug-25 | 2 | 1 | Completed
| Hot Deals Follow-Up | Yaser Mohammed | 01-Aug-25 | 01-Aug-25 | 1 | 1 | Completed
| Cold Calling Training for Hammad | Yaser Mohammed | 01-Aug-25 | 01-Aug-25 | 2 | 1 | Completed
| FreoMoney Operational setup | Yaser Mohammed | 01-Aug-25 | 01-Aug-25 | 1.5 | 2 | Completed
| CSB client Demo | Yaser Mohammed | 02-Aug-25 | 02-Aug-25 | 1 | 1 | Completed
| 10 Demos for the month to be scheduled | Pallavi Singh | 03-Aug-25 | 29-Aug-25 | 19 |  | Completed
| 10 Demos for the month to be scheduled | Yaser Mohammed | 03-Aug-25 | 29-Aug-25 | 19 |  | Completed
| BACL - Indus Login and Stab Case Allocation | Darshan LD | 04-Aug-25 | 04-Aug-25 | 1 | 1 | Completed
| AiXBFS X AiXQP - Debt Recovery Course Launch in NorthEast | Pallavi Singh | 04-Aug-25 | 22-Aug-25 |  |  | Completed
| AiXFieldGo + AiXCollectPro PPT | Pallavi Singh | 04-Aug-25 | 04-Aug-25 |  | 1 | Completed
| Drafting Email to Dr. Bandaru | Pallavi Singh | 04-Aug-25 | 04-Aug-25 |  | 1 | Completed
| BACL Ops Review - Paid Count & Total Allocation | Pallavi Singh | 04-Aug-25 | 04-Aug-25 |  | 0.5 | Completed
| AiXQP x AiXBFS - Prospectus for Launch of AI-Powered DRA Course | Pallavi Singh | 04-Aug-25 | 04-Aug-25 |  | 1 | Completed
| Freomoney Strategy discussion | Pallavi Singh | 04-Aug-25 | 04-Aug-25 | 1.5 | 1 | Completed
| Sales closure for AUG preparation | Pallavi Singh | 04-Aug-25 | 04-Aug-25 | 1 | 1 | Completed
| Bank Empanalment Discussion | Pallavi Singh | 04-Aug-25 | 04-Aug-25 | 1.5 | 0.5 | Completed
| Weekly Manager's Meeting | Pallavi Singh | 04-Aug-25 | 04-Aug-25 |  | 1 | Completed
| Trademark Registration Request – AiXFieldGo & AiXCollectPro | Pallavi Singh | 04-Aug-25 | 12-Aug-25 | 0.5 |  | Completed
| New Lead prospecting | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 2 | 2 | Completed
| Hot Leads Followup | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 0.5 | 0.5 | Completed
| Freomoney Strategy discussion | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 0.5 | 0.5 | Completed
| Daily Jira Task update for self and team | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 1 | 1 | Completed
| Sales closure for AUG preparation | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 1 | 1 | Completed
| Bank Empanalment Discussion | Yaser Mohammed | 04-Aug-25 | 04-Aug-25 | 0.5 | 0.5 | Completed
| Cold calling training with Hammad | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 1 | 1 | Completed
| Jira Task update for self and Team | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 0.5 | 0.5 | Completed
| Connect with Personal Network for Business Opportunities | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 1 | 1 | Completed
| Meeting with NABARD | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 2 | 2 | Completed
| Hot Deals FUP | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 1 | 1 | Completed
| Lead Prospecting from Mumbai Event | Yaser Mohammed | 05-Aug-25 | 05-Aug-25 | 3 | 3 | Completed
| BACL Daily standup call | Pallavi Singh | 06-Aug-25 | 06-Aug-25 | 1 | 1 | Completed
| Strategy meeting for BFS | Pallavi Singh | 06-Aug-25 | 06-Aug-25 | 1.5 | 1 | Completed
| AiXQP Preparation | Pallavi Singh | 06-Aug-25 | 06-Aug-25 | 3 | 3 | Completed
| Investor Deck Brainstorming | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 2 | 2 | Completed
| Daily Jira self and team task planning | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 0.5 |  | Completed
| Strategy meeting for BFS | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 1.5 | 1 | Completed
| Prospecting leads from Mumbai events for Demo | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 2.5 | 2.5 | Completed
| Cold calling training | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 1.5 | 1.5 | Completed
| Call with Medcare | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 1 |  | Completed
| In-Person meeting Frazer Town | Yaser Mohammed | 06-Aug-25 | 06-Aug-25 | 3 | 2.5 | Completed
| Call monitoring – BFS - Smartflow | Darshan LD | 07-Aug-25 | 07-Aug-25 | 0.5 | 0.5 | Completed
| BACL - Daily report | Darshan LD | 07-Aug-25 | 07-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 07-Aug-25 | 07-Aug-25 | 2 | 2 | Completed
| BACL - Daily Review Meeting | Darshan LD | 07-Aug-25 | 07-Aug-25 | 1 | 2 | Completed
| AiXQP Module & File Reference Document Created | Pallavi Singh | 07-Aug-25 | 07-Aug-25 | 2 | 2 | Completed
| Submitted Jul'25 DUAL PI Bills of BACL to Finance Team | Pallavi Singh | 07-Aug-25 | 08-Aug-25 |  | 0.5 | Completed
| AiXQP Launch | Pallavi Singh | 07-Aug-25 | 07-Aug-25 | 3.5 | 3 | Completed
| Meeting with CTO | Yaser Mohammed | 07-Aug-25 | 07-Aug-25 | 2 | 2 | Completed
| Cold calling training | Yaser Mohammed | 07-Aug-25 | 07-Aug-25 | 1.5 | 1.5 | Completed
| Prospecting leads for demo from Mumbai events | Yaser Mohammed | 07-Aug-25 | 07-Aug-25 | 2.5 | 2 | Completed
| In-Person Meeting NABARD | Yaser Mohammed | 07-Aug-25 | 07-Aug-25 | 3 | 3 | Completed
| BACL - Daily report | Darshan LD | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 08-Aug-25 | 08-Aug-25 | 2 | 2 | Completed
| BACL - Daily Review Meeting | Darshan LD | 08-Aug-25 | 08-Aug-25 | 1 | 2 | Completed
| Business strategy for RCM in UAE | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 1 |  | Completed
| AiXQP - Developing Quiz and Assessment for Debt Recovery Course | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 4 |  | Completed
| Reviewing AiXQP - AI Powered Debt Recovery Course AiXBFS | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| AiXQP Video Script for the Course Introduction | Pallavi Singh | 08-Aug-25 | 12-Aug-25 |  | 16 | Completed
| Reviewed BACL Performance and Updated Ranking Wise Pi TF BX Dashboard_06Aug'25 to Stakeholders | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 0.5 | 0.5 | Completed
| Financial Projections for BACL & FreoMoney | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| CLONE - Business Strategy Discussion for RCM Middle East | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 1.5 |  | Completed
| AiXQP Launch | Pallavi Singh | 08-Aug-25 | 08-Aug-25 | 3 |  | In Progress
| Business strategy for RCM in UAE | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| Partnership call with odoo | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 1 | 0.75 | Completed
| Daily Jira Task creation for self and team | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 0.5 |  | Completed
| Business Strategy Discussion for RCM Middle East | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 1.5 |  | Completed
| Email Campaign for Hot leads | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| Prospecting Mumbai event leads for Demos | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 2 | 2 | Completed
| Financial Projections for BACL & FreoMoney | Yaser Mohammed | 08-Aug-25 | 08-Aug-25 | 1 | 1 | Completed
| BACL - Daily report | Darshan LD | 09-Aug-25 | 09-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 09-Aug-25 | 09-Aug-25 | 2 | 2 | Completed
| BACL - Daily Review Meeting | Darshan LD | 09-Aug-25 | 09-Aug-25 | 1 | 2 | Completed
| Call monitoring – BFS - Smartflow | Darshan LD | 10-Aug-25 | 10-Aug-25 | 0.5 | 0.5 | Completed
| BACL - Daily report | Darshan LD | 10-Aug-25 | 10-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 10-Aug-25 | 10-Aug-25 | 2 | 2 | Completed
| BACL - Daily Review Meeting | Darshan LD | 10-Aug-25 | 10-Aug-25 | 1 | 2 | Completed
| BACL - Daily report | Darshan LD | 11-Aug-25 | 11-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 11-Aug-25 | 11-Aug-25 | 2 | 2 | Completed
| BACL - Daily Review Meeting | Darshan LD | 11-Aug-25 | 11-Aug-25 | 1 | 2 | Completed
| KMB Project | Darshan LD | 11-Aug-25 | 30-Sep-25 |  |  | In Progress
| Freo Money Project | Darshan LD | 11-Aug-25 | 30-Sep-25 |  |  | In Progress
| BACL Project | Darshan LD | 11-Aug-25 | 30-Sep-25 |  |  | In Progress
| Call with Altruist for commercial discussion | Pallavi Singh | 11-Aug-25 | 11-Aug-25 | 0.5 |  | Completed
| Weekly Managers meeting | Pallavi Singh | 11-Aug-25 | 11-Aug-25 | 0.75 |  | Completed
| Sales and Strategy Technical Interview - Deepak | Yaser Mohammed | 11-Aug-25 | 11-Aug-25 | 0.75 |  | To Do
| Sales and Strategy Technical Interview - Shaik Ibraheem | Yaser Mohammed | 11-Aug-25 | 11-Aug-25 | 0.75 | 0.75 | Completed
| Project Planning Self & Team | Yaser Mohammed | 11-Aug-25 | 30-Sep-25 | 4.5 | 2.5 | To Do
| Jira Quarterly Planning | Yaser Mohammed | 11-Aug-25 | 11-Aug-25 | 2 |  | To Do
| Weekly Managers meeting | Yaser Mohammed | 11-Aug-25 | 11-Aug-25 | 0.75 | 0.75 | Completed
| AiXFieldGo/Collect Pro Project - Business Development - Q3 | Yaser Mohammed | 11-Aug-25 | 30-Sep-25 | 403.6667 | 92.25 | To Do
| BFS Debt Collection Project Q3 | Yaser Mohammed | 11-Aug-25 | 30-Sep-25 | 383.8333 | 116.0833 | To Do
| BACL operational activity | Darshan LD | 12-Aug-25 | 12-Aug-25 | 2 | 2 | Completed
| Daily Standup BACL- BLR | Darshan LD | 12-Aug-25 | 12-Aug-25 | 1 | 1 | Completed
| BACL- Daily Review Call | Darshan LD | 12-Aug-25 | 12-Aug-25 | 1 | 2 | Completed
| Business Presentation - AiXQP | Pallavi Singh | 12-Aug-25 | 13-Aug-25 |  | 5 | Completed
| Case Study - AiXQP | Pallavi Singh | 12-Aug-25 | 14-Aug-25 | 3 |  | Completed
| BACL - Operational activity | Darshan LD | 13-Aug-25 | 13-Aug-25 | 2 | 2.5 | Completed
| One to One meeting with the team - BLR | Darshan LD | 13-Aug-25 | 13-Aug-25 | 1 | 1 | Completed
| BACL- Daily Review Call | Darshan LD | 13-Aug-25 | 13-Aug-25 | 1 | 1.5 | Completed
| Interview Mira - Sales & Strategic Partnership, CTO Office | Pallavi Singh | 13-Aug-25 | 13-Aug-25 | 1 | 1 | Completed
| White Paper - AiXQP | Pallavi Singh | 13-Aug-25 | 14-Aug-25 |  | 4 | Completed
| Dual PI Allocation | Darshan LD | 14-Aug-25 | 18-Aug-25 | 1 | 0.83333 | Completed
| BACL - Daily report | Darshan LD | 14-Aug-25 | 14-Aug-25 | 1 | 1 | Completed
| BACL operational activity | Darshan LD | 14-Aug-25 | 14-Aug-25 | 2 | 2 | Completed
| BACL- Daily Review Call | Darshan LD | 14-Aug-25 | 14-Aug-25 | 1 | 1.5 | Completed
| Technical Presentation - AiXQP | Pallavi Singh | 14-Aug-25 | 14-Aug-25 |  | 5 | To Do
| AiXQP Meeting with Nikilesh - White Paper, Case Studies, and Website Changes | Pallavi Singh | 15-Aug-25 | 15-Aug-25 |  | 0.5 | Completed
| Had a call with KMB - documentation | Darshan LD | 18-Aug-25 | 18-Aug-25 | 0.5 | 0.5 | Completed
| BACL - Daily report | Darshan LD | 18-Aug-25 | 18-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 18-Aug-25 | 18-Aug-25 | 2 | 2 | Completed
| One to One meeting with the team - ASM | Darshan LD | 18-Aug-25 | 18-Aug-25 | 2 |  | Completed
| Weekly Manager's Meeting | Pallavi Singh | 18-Aug-25 | 18-Aug-25 |  | 1.5 | Completed
| AiXQP Business Presentation Review | Pallavi Singh | 18-Aug-25 | 18-Aug-25 |  | 0.5 | Completed
| AiXQP Case Study Creation | Pallavi Singh | 18-Aug-25 | 18-Aug-25 |  | 3 | Completed
| AiXQP White Paper Creation | Pallavi Singh | 18-Aug-25 | 18-Aug-25 |  | 3 | Completed
| AiXQP Brochure Creation | Pallavi Singh | 18-Aug-25 | 18-Aug-25 |  | 3 | Completed
| BACL - Daily report | Darshan LD | 19-Aug-25 | 19-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 19-Aug-25 | 19-Aug-25 | 2.5 | 2.5 | Completed
| Standup call with Assam team | Darshan LD | 19-Aug-25 | 19-Aug-25 | 0.5 | 0.5 | Completed
| Meeting with CTO, Mr. Rohim regarding StarAgile and AiXQP Course and LMS | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  | 2 | Completed
| Meeting with StarAgile Thought Leadership | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  | 1 | Completed
| Bi-weekly Sync Call with Mr. Aaron | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  |  | Completed
| Meeting with Rohim Sir regarding AiXQP LMS Course Change | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  | 2 | Completed
| Bi-weekly sync up call with Mr. Aaron | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  | 0.5 | Completed
| AiXBFS X AiXQP - Meeting with Assam Team for Launch | Pallavi Singh | 19-Aug-25 | 19-Aug-25 |  | 2 | Completed
| Bajaj Bangalore Office Visit - Plan Creation | Pallavi Singh | 19-Aug-25 | 20-Aug-25 |  | 1.5 | Completed
| CSB Bank Follow-up Call | Yaser Mohammed | 19-Aug-25 | 19-Aug-25 | 1 | 0.75 | Completed
| NABARD Call | Yaser Mohammed | 19-Aug-25 | 19-Aug-25 | 0.5 | 0.5 | Completed
| Altruist Call | Yaser Mohammed | 19-Aug-25 | 19-Aug-25 | 1 | 0.5 | Completed
| Weekly meeting with Aaron | Yaser Mohammed | 19-Aug-25 | 19-Aug-25 | 0.75 | 0.75 | Completed
| D&O policy - quotes & Coverage PPT | Darshan LD | 20-Aug-25 | 20-Aug-25 | 1 | 1 | Completed
| BACL - Daily report | Darshan LD | 20-Aug-25 | 20-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 20-Aug-25 | 20-Aug-25 | 2.5 | 2.5 | Completed
| Review AI Component features for AIXQP | Pallavi Singh | 20-Aug-25 | 20-Aug-25 |  | 1 | Completed
| Created AI based features for AIXQP LMS | Pallavi Singh | 20-Aug-25 | 20-Aug-25 |  | 2 | Completed
| Reviewed AI Requirement of AiXQP LMS | Pallavi Singh | 20-Aug-25 | 20-Aug-25 |  | 2 | Completed
| Created BRD for AiXQP LMS | Pallavi Singh | 20-Aug-25 | 22-Aug-25 |  | 2 | Completed
| Operational activity | Darshan LD | 21-Aug-25 | 21-Aug-25 | 2 | 2 | Completed
| BACL - Daily report | Darshan LD | 21-Aug-25 | 21-Aug-25 | 1 | 1 | Completed
| In person meeting with Bajaj & ITcart Team | Darshan LD | 21-Aug-25 | 21-Aug-25 | 1 | 2.5 | Completed
| Meeting with Mr. Jeff for review and update meeting of AiXBFS | Pallavi Singh | 21-Aug-25 | 21-Aug-25 |  | 0.5 | Completed
| Conversational AI Demo Clip Review created by our AI Team | Pallavi Singh | 21-Aug-25 | 21-Aug-25 |  | 1 | Completed
| LMS Blueprint incorporating AI Features | Pallavi Singh | 21-Aug-25 | 22-Aug-25 |  | 2 | Completed
| In-Person Meeting with Bajaj Zonal Manager | Pallavi Singh | 21-Aug-25 | 21-Aug-25 |  | 4 | Completed
| Resume shortlisting for Sales & Strategic Partnerships Executive | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 1.5 | 1.5 | Completed
| Call with GrayQuest | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 1 | 1 | Completed
| Cold Calling Training | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 1.5 | 1.5 | Completed
| Hot deals Follow-up | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 2.5 | 2 | Completed
| Weekly meeting with Jeff and Aaron | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 1 | 0.75 | Completed
| BACL Client Meeting In-Person at iTCart | Yaser Mohammed | 21-Aug-25 | 21-Aug-25 | 3 | 3 | Completed
| Dialer training session - Assam | Darshan LD | 22-Aug-25 | 22-Aug-25 | 1 | 2.25 | Completed
| BACL - Daily report | Darshan LD | 22-Aug-25 | 22-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 22-Aug-25 | 22-Aug-25 | 2 | 2 | Completed
| GrayQuest Pricing Proposal Created for Debt Recovery Managed Services | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1 | Completed
| Meeting with L&T Finance for Product Demo | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 2 | Completed
| Meeting with Altruist for Pricing Discussion | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 0.5 | Completed
| Call with GrayQuest Team | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 0.5 | Completed
| GrayQuest Payout Grid Creation including Strategy | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 0.5 | Completed
| Master Tracker Creation for AiXQP Launch | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1 | Completed
| Post-Meeting Discussion with Technical Team and HOD regarding Altruist Requirement | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1.5 | Completed
| Pre-Meeting Discussion with Yaser regarding Pitch for L&T | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 0.5 | Completed
| Discussion with Yaser regarding Slab Based Pricing for Altruist | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 0.5 | Completed
| Meeting with Altruist regarding Pricing Proposal | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1 | Completed
| Meeting with L&T regarding Empanelment and Product Demo | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1.5 | Completed
| Business Presentation Changes based on recent approval | Pallavi Singh | 22-Aug-25 | 22-Aug-25 |  | 1 | Completed
| Call with GrayQuest Team | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| GrayQuest Payout Grid Creation including Strategy | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| Post-Meeting Discussion with Technical Team and HOD regarding Altruist Requirement | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| Pre-Meeting Discussion with Pallavi regarding Pitch for L&T | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| Price Discussion for Altruist | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| Meeting with Altruist regarding Pricing Proposal | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| Meeting with L&T regarding Empanelment and Product Demo | Yaser Mohammed | 22-Aug-25 | 22-Aug-25 |  |  | Completed
| BACL - Daily report | Darshan LD | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 25-Aug-25 | 25-Aug-25 | 2 | 2 | Completed
| Standup call with team Assam | Darshan LD | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Weekly Manager's Meeting | Pallavi Singh | 25-Aug-25 | 25-Aug-25 |  | 1.5 | Completed
| Reviewed AI for Developer Course for AiXQP | Pallavi Singh | 25-Aug-25 | 25-Aug-25 |  | 2 | Completed
| Upload the Training Modules in the AiXQP Sharepoint | Pallavi Singh | 25-Aug-25 | 29-Aug-25 |  | 16 | Completed
| Update internal tracker for the AiXQP Launch | Pallavi Singh | 25-Aug-25 | 25-Aug-25 |  |  | Completed
| Meeting scheduled with College to discuss about the course | Pallavi Singh | 25-Aug-25 | 25-Aug-25 |  |  | Completed
| Update Master Tracker for AiXQP Launch Planning | Pallavi Singh | 25-Aug-25 | 25-Aug-25 |  | 1 | Completed
| Review with Hammad on the SDR calling for the day | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 0.5 |  | Completed
| Weekly manager connect | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Deal Pipeline email to Management | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 0.5 | 0.5 | Completed
| FSR Creation | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Connect with Team | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Hot Leads Followup | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 1.5 | 1.5 | Completed
| Call with GrayQuest | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 0.5 | 0.5 | Completed
| Jira Task update | Yaser Mohammed | 25-Aug-25 | 25-Aug-25 | 1 | 1 | Completed
| Call monitoring – BFS - Smartflow | Darshan LD | 26-Aug-25 | 26-Aug-25 | 0.5 | 0.5 | Completed
| BACL - Daily report | Darshan LD | 26-Aug-25 | 26-Aug-25 | 1 | 1 | Completed
| Daily standup call with team Assam | Darshan LD | 26-Aug-25 | 26-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 26-Aug-25 | 26-Aug-25 | 2 | 2 | Completed
| Email Campaign for AiXBFS Product Discussion with Yaser | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  | 1 | Completed
| CRM Update | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  | 1 | Completed
| Post-Meeting discussion of RTV In-Person Meeting | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  | 1.5 | Completed
| Discussion with Syed and Assam Team for Early Launch Planning | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  | 0.5 | Completed
| Bi-weekly Sync Call with Mr. Aaron | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  |  | Completed
| Meeting with RTV for Student Enrollment | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  |  | Completed
| Conversational AI and Product Demo - BACL Team | Pallavi Singh | 26-Aug-25 | 26-Aug-25 |  | 1 | Completed
| AiXQP Website Update | Pallavi Singh | 26-Aug-25 | 26-Aug-25 | 1 |  | Completed
| Bi-weekly Sync Call with Mr. Aaron | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 0.5 | 0.5 | Completed
| Demos Schedule for AiXFieldGo&CollectPro | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 2.5 | 2.5 | Completed
| Connect with CSB Bank | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 0.5 | 0.5 | Completed
| Self Task update | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 0.5 | 0.5 | Completed
| Reconnect with Vivifi | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 0.5 | 0.5 | Completed
| BACL Demo of AiXFieldGo & CollectPro | Yaser Mohammed | 26-Aug-25 | 26-Aug-25 | 1 | 1 | Completed
| BACL - Daily report | Darshan LD | 27-Aug-25 | 27-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 27-Aug-25 | 27-Aug-25 | 2 | 2 | Completed
| Daily standup call with team Assam | Darshan LD | 27-Aug-25 | 27-Aug-25 | 0.5 | 1 | Completed
| Redo of Business Presentation - AiXQP | Pallavi Singh | 27-Aug-25 | 29-Aug-25 |  | 2.5 | Completed
| Discussion with Assam Team to discuss RTV Strategy - AiXQP | Pallavi Singh | 27-Aug-25 | 27-Aug-25 |  | 1 | Completed
| AiXQP Course Upload in the Website | Pallavi Singh | 27-Aug-25 | 02-Sep-25 | 4 |  | Completed
| Connect with SurePass for partnership Synergies | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 1 | 1 | Completed
| Jira Task Update | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 0.5 | 0.5 | Completed
| Connect with Tech team on Product development and flow | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 0.5 | 0.5 | Completed
| Meeting with Jeff | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 0.5 | 0.5 | Completed
| Email Strategy for Lead generation | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 1.5 | 1.5 | Completed
| Sales projections creation | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 2 | 2 | Completed
| Interview for Sales and Strategy Candidate Founders Office | Yaser Mohammed | 27-Aug-25 | 27-Aug-25 | 1 | 1 | Completed
| Daily standup call with team Assam & AIXQP discussion with Mrs.Nafisa & Mr. Ilius | Darshan LD | 28-Aug-25 | 28-Aug-25 | 0.5 | 1 | Completed
| AiXQP Challenges Addressed | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 2 | Completed
| AiXQP Questionnaire Document Created | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 1.5 | Completed
| Weekly Sync Meeting with CEO, Mr. Jeff for review and updates | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 0.5 | Completed
| AiXQP Challenges Discussion with Assam Team | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 1 | Completed
| Discussion about AiXQP Candidate Enrolment | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 1 | Completed
| Discussion with the Marketing Manager for GTM Strategy | Pallavi Singh | 28-Aug-25 | 28-Aug-25 |  | 2 | Completed
| Interview feedback for candidate Mrudal | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.5 | 0.33333 | Completed
| AiXQP Call | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.75 | 0.75 | Completed
| Interview for Sales, strategy and Partnership executive for Founders Office | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 1 | 1 | Completed
| Bi- Weekly call with Jeff | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.75 | 0.75 | Completed
| Follow-up with GrayQuest for empanelment | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.33333 | 0.33333 | Completed
| Follow-up with Altruist for Commercials | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.16667 | 0.16667 | Completed
| Follow-up with CSB Bank | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.5 | 0.5 | Completed
| Follow-up with FreoMoney for Code generation | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.5 | 0.5 | Completed
| Email Campaign for FieldGo & CollectPro Lead generation | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 1 | 1 | Completed
| Self Jira Task update | Yaser Mohammed | 28-Aug-25 | 28-Aug-25 | 0.5 | 0.5 | Completed
| Call monitoring – BFS - Smartflow | Darshan LD | 29-Aug-25 | 29-Aug-25 | 0.5 | 0.5 | Completed
| BACL - Daily report | Darshan LD | 29-Aug-25 | 29-Aug-25 | 1 | 1 | Completed
| Operational activity | Darshan LD | 29-Aug-25 | 29-Aug-25 | 2 | 2 | Completed
| Daily standup call with team Assam | Darshan LD | 29-Aug-25 | 29-Aug-25 | 0.5 | 1 | Completed
| Interview feedback for candidate Parul | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 0.5 | 0.5 | Completed
| Sales projections for the next quarter | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 2 | 2 | Completed
| Connect with Ankur from BACL | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 0.5 | 0.5 | Completed
| Follow-Up With Altruist | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 0.5 | 0.33333 | Completed
| Connect with Hammad | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 1.5 | 1.5 | Completed
| Self Jira Task Update | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 0.5 | 0.5 | Completed
| Interview for Sales, strategy and Partnership executive for Founders Office | Yaser Mohammed | 29-Aug-25 | 29-Aug-25 | 1 | 1 | Completed