## 2025-Aug-Utilisation
Resources | Planned Utilization |  | Billable Utilization |  | Non Billable Utilization |  | Attendance Recorded |  | Leaves Recorded |  | LOP Recorded |  | Overall Utilization
Resource Name | Planned (Hrs) | Planned (%) | Actual (Hrs) | Actual (%) | Non-Billable (Hrs) | Non-Billable (%) | Attendance (Hrs) | Attendance (%) | Leaves (Hrs) | Leaves (%) | LOP (Hrs) | LOP (%) | Overtime (Hrs) | Total Utilization
Syed Ali | 160 | 100% | 148 | 92.5% | 24.75 | 16.72% | 148 | 92.5% | 12 | 7.5% | 8 | 0% |  | 92.5%
Fathima Rahna | 160 | 100% | 136 | 85% | 16.75 | 12.68% | 136 | 85% | 24 | 15% | 16 | 0% |  | 85%

## 2025-Aug-Task
Module / Category | Task Details | Assigned To | Start Date | Due Date | Planned (Hrs) | Actual (Hrs) | Status | End Date | Risk / Comments / Comp Off
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-01 | 2025-08-01 | 0.25 | 0.25 | Completed | 2025-08-01
Meeting | Daily Standup GRC+QMS | Syed Ali Hussain | 2025-08-01 | 2025-08-01 | 0.25 | 0.25 | Completed | 2025-08-01
Jira Prod | Meeting with Syed Sir regarding Devops and Marketing Jira paln | Syed Ali Hussain | 2025-08-01 | 2025-08-01 | 0.5 | 0.5 | Completed | 2025-08-01
Project Managerial Task | Planning and structuring JIRA | Syed Ali Hussain | 2025-08-01 | 2025-08-01 | 5 | 5 | Completed | 2025-08-01
Meeting | All Employees Meeting with Rohim sir | Syed Ali Hussain | 2025-08-01 | 2025-08-01 | 2 | 2 | Completed | 2025-08-01
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 0.25 | 0.25 | Completed | 2025-08-04
Meeting | All Managers Meeting | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 1 | 1 | Completed | 2025-08-04
Meeting | Dev Ops Department Meeting with Mr Rohim Sir | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 1 | 1 | Completed | 2025-08-04
Meeting | Marketing Department Meeting with Mr Rohim Sir | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 2 | 2 | Completed | 2025-08-04
Progect Managerial Task | Creating a plan for JIRA updation for Dev Ops team | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 4 | 2.75 | Completed | 2025-08-04
Meeting | Meeting with Dev Ops leads for JIRA | Syed Ali Hussain | 2025-08-04 | 2025-08-04 | 1 | 1 | Completed | 2025-08-04
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-05 | 2025-08-05 | 0.25 | 0.25 | Completed | 2025-08-05
Progect Managerial Task | Creating a step by step guide of JIRA updation for Marketing Ops team | Syed Ali Hussain | 2025-08-05 | 2025-08-05 | 4 | 4.75 | Completed | 2025-08-05
Meeting | Meeting with Marketing Ops leads for JIRA | Syed Ali Hussain | 2025-08-05 | 2025-08-05 | 1 | 1 | Completed | 2025-08-05
Meeting | All Managers Meeting- With Mr Rohim | Syed Ali Hussain | 2025-08-05 | 2025-08-05 | 1 | 1 | Completed | 2025-08-05
Meeting | Farewell for Farkhanda and Ifla | Syed Ali Hussain | 2025-08-05 | 2025-08-05 | 1 | 1 | Completed | 2025-08-05
Project Managerial Task | Gap Assessment of HRD JIRA | Syed Ali Hussain | 2025-08-06 | 2025-08-06 | 2 | 1.5 | Completed | 2025-08-06
Project Managerial Task | Created step by step guide for HR department JIRA | Syed Ali Hussain | 2025-08-06 | 2025-08-06 | 2 | 2 | Completed | 2025-08-06
Project Managerial Task | Created the plan for Devops in Jira | Syed Ali Hussain | 2025-08-06 | 2025-08-06 | 1 | 0.5 | Completed | 2025-08-06
AiX Collect Pro | Review- Test cases of AiX Collect Pro. | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 4 | 3.75 | Completed | 2025-08-07
Project Managerial Task | Meeting With Nikhilesh for Marketing Ops JIRA. | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 0.5 | 0.5 | Completed | 2025-08-07
Project Managerial Task | Created step by step guide for Finance and Accounts department JIRA | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 2 | 2 | Completed | 2025-08-07
Project Managerial Task | Updated step by step guide for HR department JIRA | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 1 | 1 | Completed | 2025-08-07
Project Managerial Task | Meeting With Arjun for Finance and Accounts JIRA. | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 0.5 | 0.5 | Completed | 2025-08-07
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-07 | 2025-08-07 | 0.25 | 0.25 | Completed | 2025-08-07
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-08 | 2025-08-08 | 0.25 | 0.25 | Completed | 2025-08-08
Progect Managerial Task | Solving Jira updation issues for Dev Ops and Marketing Department. | Syed Ali Hussain | 2025-08-08 | 2025-08-08 | 1 | 0.75 | Completed | 2025-08-08
Progect Managerial Task | Created step by step guide for GRC Ops department JIRA | Syed Ali Hussain | 2025-08-08 | 2025-08-08 | 2 | 3 | Completed | 2025-08-08
Project Managerial Task | Created step by step guide for BFS department JIRA | Syed Ali Hussain | 2025-08-08 | 2025-08-08 | 2 | 3 | Completed | 2025-08-08
Meeting | Created the FSR Report for (28/07/2025 - 08/08/2025) | Syed Ali Hussain | 2025-08-08 | 2025-08-08 | 1 | 1 | Completed | 2025-08-08
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-11 | 2025-08-11 | 0.25 | 0.25 | Completed | 2025-08-11
Meeting | All Managers Meeting | Syed Ali Hussain | 2025-08-11 | 2025-08-11 | 1 | 1 | Completed | 2025-08-11
Project Managerial Task | Research on creating the Bar Chart for utilisation for all departments. | Syed Ali Hussain | 2025-08-11 | 2025-08-11 | 3 | 2.75 | Completed | 2025-08-11
Project Managerial Task | Meeting with HRD for JIRA. | Syed Ali Hussain | 2025-08-11 | 2025-08-11 | 1 | 1 | Completed | 2025-08-11
AiX Collect Pro | Test Case Review- AiX Collect Pro | Syed Ali Hussain | 2025-08-11 | 2025-08-11 | 2 | 3 | Completed | 2025-08-11
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-12 | 2025-08-12 | 0.25 | 0.25 | Completed | 2025-08-12
Project Managerial Task | Creating the Bar Chart for utilisation for all departments | Syed Ali Hussain | 2025-08-12 | 2025-08-12 | 3 | 2.75 | Completed | 2025-08-12
Project Managerial Task | Meeting Ms. Nafisa and Mr. Ilius for JIRA Training | Syed Ali Hussain | 2025-08-12 | 2025-08-12 | 1 | 1 | Completed | 2025-08-12
AiX Collect Pro | Exploratory Testing – AiX Collect Pro Dashboard | Syed Ali Hussain | 2025-08-12 | 2025-08-12 | 2 | 2 | Completed | 2025-08-12
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Team management page | Syed Ali Hussain | 2025-08-12 | 2025-08-12 | 2 | 2 | Completed | 2025-08-12
Project Managerial Task | Creating the utilisation for Finance and Accounts, HRD , GRC and BFS Departments exported from JIRA | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 2 | 1.5 | Completed | 2025-08-13
Meeting | Meeting with Backend developers. | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 0.5 | 0.5 | Completed | 2025-08-13
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Task management page | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 2 | 1.5 | Completed | 2025-08-13
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Collection Metrics page | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 2 | 1 | Completed | 2025-08-13
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Alerts and Escalation page | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 1 | 1 | Completed | 2025-08-13
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Attendance and Leave page | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 1 | 1 | Completed | 2025-08-13
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Documents page | Syed Ali Hussain | 2025-08-13 | 2025-08-13 | 2 | 1.5 | completed | 2025-08-13
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 0.25 | 0.25 | Completed | 2025-08-14
AiX Field Go | Exploring AiX Field Go APIs document. | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 4 | 2.75 | Completed | 2025-08-14
Project Managerial Task | Jira Training for CurlyBrace Team | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 0.5 | 0.5 | Completed | 2025-08-14
AiX Field Go | KT meeting for AiX Field Go API testing with Numan | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 1 | 1.5 | Completed | 2025-08-14
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Settings page | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 1 | 1 | Completed | 2025-08-14
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - Reports page | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 1 | 1 | Completed | 2025-08-14
AiX Collect Pro | Exploratory Testing – AiX Collect Pro - AI Insight page | Syed Ali Hussain | 2025-08-14 | 2025-08-14 | 1 | 1 | Completed
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-18 | 2025-08-18 | 0.25 | 0.25 | Completed | 2025-08-18
Meeting | KT session with Krushangi, Shuaib and Syed Sir | Syed Ali Hussain | 2025-08-18 | 2025-08-18 | 3.5 | 3.5 | Completed | 2025-08-18
AiX Field Go | API Testing- User and Authentication APIs- AiX Field Go | Syed Ali Hussain | 2025-08-18 | 2025-08-18 | 2.25 | 2.25 | Completed | 2025-08-18
AiX Field Go | API Testing- Attendance APIs- AiX Field Go | Syed Ali Hussain | 2025-08-18 | 2025-08-18 | 2 | 2 | Completed | 2025-08-18
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 0.25 | 0.25 | Completed | 2025-08-20
AiX Field Go | API Testing -Attendance APIs- AiX Field Go | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 4 | 2 | Completed | 2025-08-20
AiX Field Go | API Testing - APIs of Dashboard- AiX Field Go | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 2 | 2 | Completed | 2025-08-20
AiX Field Go | Meeting -API Testing Issues- AiX Field Go | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 2 | 1 | Completed | 2025-08-20
Meeting | Jira Training for Mr. Shuaib | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 0.5 | 0.5 | Completed | 2025-08-20
QA Managerial Task | Researching on Live mobile testing tools (Browser Stack) | Syed Ali Hussain | 2025-08-20 | 2025-08-20 | 2.25 | 2.25 | Completed | 2025-08-20
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-21 | 2025-08-21 | 0.25 | 0.25 | Completed | 2025-08-21
Meeting | Daily Scrum | Syed Ali Hussain | 2025-08-21 | 2025-08-21 | 0.5 | 0.5 | Completed | 2025-08-21
AiX Field Go | API Testing - APIs of Tasks and Dashboard- AiX Field Go | Syed Ali Hussain | 2025-08-21 | 2025-08-21 | 4 | 4.75 | Completed | 2025-08-21
Project Managerial Task | Creating the utilisation report of all departments from Jira | Syed Ali Hussain | 2025-08-21 | 2025-08-21 | 2 | 2 | Completed | 2025-08-21
AiX Field Go | Meeting with the backend team (Curly Brace) | Syed Ali Hussain | 2025-08-21 | 2025-08-21 | 0.5 | 0.5 | Completed | 2025-08-21
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 0.25 | 0.25 | Completed | 2025-08-22
Meeting | Daily Scrum | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 0.25 | 0.25 | Completed | 2025-08-22
AiX Field Go | API Testing- KYC APIs- AiX Field Go | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 4 | 4 | Completed | 2025-08-22
Meeting | FSR Prepration (11-08-25 to 22-08-25) | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 1 | 1 | Completed | 2025-08-22
AiX Field Go | Meeting with Vineet for API issues. | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 0.5 | 0.5 | Completed | 2025-08-22
AiX Field Go | API Testing- Collection APIs- AiX Field Go | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 4 | 1.75 | Completed | 2025-08-22
Meeting | Meeting with Syed Sir regarding AiX Field Go And Collect Pro | Syed Ali Hussain | 2025-08-22 | 2025-08-22 | 0.5 | 0.5 | Completed | 2025-08-22
Project Managerial Task | Creating Sprint Report- 11/08/2025 to 22/08/2025- All Departments | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 1 | 1 | Completed | 2025-08-25
AiX Field Go | API Testing- Summary APIs- AiX Field Go | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 2 | 1.5 | Completed | 2025-08-25
AiX Field Go | API Testing- Collection APIs- AiX Field Go | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 2 | 2.25 | Ongoing | 2025-08-25
Project Managerial Task | Creating Report on QA/ Project Management implementations. | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 2 | 2 | Completed | 2025-08-25
Meeting | All Managers Meeting (25-08-2025) | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 1 | 1 | Completed | 2025-08-25
Meeting | DailyStandup | Syed Ali Hussain | 2025-08-25 | 2025-08-25 | 0.25 | 0.25 | Completed | 2025-08-25
Meeting | Daily Scrum (26-08-2025) | Syed Ali Hussain | 2025-08-26 | 2025-08-26 | 0.5 | 0.5 | Ongoing | 2025-08-26
AiX Field Go | Retesting API Issues/Bugs- AiX Field Go | Syed Ali Hussain | 2025-08-26 | 2025-08-26 | 4 | 3.5 | Completed | 2025-08-26
AiX Field Go | API Testing- Summary APIs- AiX Field Go | Syed Ali Hussain | 2025-08-26 | 2025-08-26 | 2 | 2 | Completed | 2025-08-26
Project Managerial Task | Jira Demo for Sabreena | Syed Ali Hussain | 2025-08-26 | 2025-08-26 | 1 | 1 | Completed | 2025-08-26
AiX Field Go | API Testing -Attendance APIs- AiX Field Go | Syed Ali Hussain | 2025-08-26 | 2025-08-26 | 1 | 1 | Completed
AiX Field Go | Meeting with Vineet regarding leave and regularization scenarios | Syed Ali Hussain | 2025-08-27 | 2025-08-27 | 0.5 | 0.5 | Completed | 2025-08-27
AiX Field Go | Retesting API Issues/Bugs- AiX Field Go | Syed Ali Hussain | 2025-08-27 | 2025-08-27 | 2.75 | 2.75 | Completed | 2025-08-27
AiX Field Go | API Testing- Negative Scenario- AiX Field Go | Syed Ali Hussain | 2025-08-27 | 2025-08-27 | 4 | 4.75 | Completed | 2025-08-27
Meeting | Daily Standup | Syed Ali Hussain | 2025-08-28 | 2025-08-28 | 0.25 | 0.25 | Completed | 2025-08-28
AiX Field Go | Meeting with Vineet regarding 502 error-AiX Field Go app | Syed Ali Hussain | 2025-08-28 | 2025-08-28 | 0.25 | 0.25 | Completed | 2025-08-28
AiX Field Go | AiX Field Go- APIs Flow Discussion | Syed Ali Hussain | 2025-08-28 | 2025-08-28 | 1 | 1 | Completed | 2025-08-28
AiX Field Go | API Testing- Negative Scenario- AiX Field Go | Syed Ali Hussain | 2025-08-28 | 2025-08-28 | 7 | 6.5 | Completed | 2025-08-28
Meeting | Daily Standup QA | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 0.25 | 0.25 | Completed | 2025-08-29
AiX Field Go | AiX Field Go- APIs Flow Discussion | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 1 | 1 | Completed | 2025-08-29
AiX Field Go | API Testing- Negative Scenario- AiX Field Go | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 4 | 4.25 | Completed | 2025-08-29
Utilisation Reort | Creating Utilisation Report- QA Department- AUG | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 1 | 1 | Completed | 2025-08-29
Meeting | Meeting with Syed Sir. | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 0.5 | 0.5 | Completed | 2025-08-29
AiX Field Go | Testing the login functionality of AiX Field Go app | Syed Ali Hussain | 2025-08-29 | 2025-08-29 | 1 | 1 | Ongoing | 2025-08-29
Meeting | Standup (GRC+QMS) | Fathima Rahna | 2025-08-01 | 2025-08-01 | 0.25 | 0.25 | Completed | 2025-08-01
Meeting | Standup (QA) | Fathima Rahna | 2025-08-01 | 2025-08-01 | 0.25 | 0.25 | Completed | 2025-08-01
AiX Collect Pro | Requirement Analysis and Test case writing for Documents Page-AIX BFS Collect Pro | Fathima Rahna | 2025-08-01 | 2025-08-01 | 3 | 3 | Completed | 2025-08-01
AiX Collect Pro | Requirement Analysis and Test case writing for Issue Logged Page-AIX BFS Collect Pro | Fathima Rahna | 2025-08-01 | 2025-08-01 | 2 | 2 | Completed | 2025-08-01
Meeting | Meeting with Founder | Fathima Rahna | 2025-08-01 | 2025-08-01 | 2.5 | 2.5 | Completed | 2025-08-01
Meeting | Standup (QA) | Fathima Rahna | 2025-08-04 | 2025-08-04 | 0.25 | 0.25 | Completed | 2025-08-04
AiX Collect Pro | Requirement Analysis and Test case writing for Alerts and Escalations, Attendance and Leave Pages-AIX BFS Collect Pro | Fathima Rahna | 2025-08-04 | 2025-08-04 | 4 | 4 | Completed | 2025-08-04
AiX Collect Pro | Requirement Analysis and Test case writing for AI Insights, Reports Pages-AIX BFS Collect Pro | Fathima Rahna | 2025-08-04 | 2025-08-04 | 3.75 | 3.75 | Completed | 2025-08-04
Meeting | Standup (QA) | Fathima Rahna | 2025-08-05 | 2025-08-05 | 0.25 | 0.25 | Completed | 2025-08-05
AiX Collect Pro | Requirement Analysis and Test case writing for Access Control page-AIX BFS Collect Pro | Fathima Rahna | 2025-08-05 | 2025-08-05 | 4 | 4 | Completed | 2025-08-05
AiX Collect Pro | Requirement Analysis and Test case writing for Settings page-AIX BFS Collect Pro | Fathima Rahna | 2025-08-05 | 2025-08-05 | 2.75 | 2.75 | Completed | 2025-08-05
Meeting | Farewell meeting | Fathima Rahna | 2025-08-05 | 2025-08-05 | 1 | 1 | Completed | 2025-08-05
AiX Collect Pro | Requirement Analysis and Test case writing Settings page-AIX BFS Collect Pro | Fathima Rahna | 2025-08-06 | 2025-08-06 | 4 | 4 | Completed | 2025-08-06
AiX Field Go | Exploratory Testing- AiX BFS Field Go | Fathima Rahna | 2025-08-06 | 2025-08-06 | 2 | 2 | Completed | 2025-08-06
AiX Collect Pro | Test case updation for AiX BFS Collect pro | Fathima Rahna | 2025-08-06 | 2025-08-06 | 2 | 2 | Completed | 2025-08-06
Meeting | Standup (QA) | Fathima Rahna | 2025-08-07 | 2025-08-07 | 0.25 | 0.25 | Completed | 2025-08-07
GRCQMS | Risk Management Report for Finance | Fathima Rahna | 2025-08-07 | 2025-08-07 | 4 | 4 | Completed | 2025-08-07
AiX Field Go | Exploratory Testing- AiX BFS Field Go | Fathima Rahna | 2025-08-07 | 2025-08-07 | 3.75 | 3.75 | Completed | 2025-08-07
Meeting | Standup (QA) | Fathima Rahna | 2025-08-08 | 2025-08-08 | 0.25 | 0.25 | Completed | 2025-08-08
AiX Collect Pro | Creating Regression Checklist for Collect Pro | Fathima Rahna | 2025-08-08 | 2025-08-08 | 4 | 4 | Completed | 2025-08-08
AiX Field Go | Creating Regression Checklist for Field Go | Fathima Rahna | 2025-08-08 | 2025-08-08 | 3.75 | 3.75 | Completed | 2025-08-08
Meeting | Standup (QA) | Fathima Rahna | 2025-08-11 | 2025-08-11 | 0.25 | 0.25 | Completed | 2025-08-11
AiX Collect Pro | Exploratory Testing for Task Management and Collection metrics pages- AiX BFS Collect Pro | Fathima Rahna | 2025-08-11 | 2025-08-11 | 3.75 | 3.75 | Completed | 2025-08-11
AiX Collect Pro | Exploratory Testing for Dashboard and Team management pages- AiX BFS Collect Pro | Fathima Rahna | 2025-08-11 | 2025-08-11 | 4 | 4 | Completed | 2025-08-11
AiX Collect Pro | Exploratory Testing for Documents, Alerts and Escalation and Attendance and Leave pages- AiX BFS Collect Pro | Fathima Rahna | 2025-08-12 | 2025-08-12 | 4 | 4 | Completed | 2025-08-12
Meeting | Standup (QA) | Fathima Rahna | 2025-08-12 | 2025-08-12 | 0.25 | 0.25 | Completed | 2025-08-12
AiX Collect Pro | Exploratory Testing forAI Insights, Reports and Settings pages- AiX BFS Collect Pro | Fathima Rahna | 2025-08-12 | 2025-08-12 | 3.75 | 3.75 | Completed | 2025-08-12
Meeting | KT meeting for API testing with Numan | Fathima Rahna | 2025-08-14 | 2025-08-14 | 1 | 1 | Completed | 2025-08-14
Meeting | Standup (QA) | Fathima Rahna | 2025-08-14 | 2025-08-14 | 0.25 | 0.25 | Completed | 2025-08-14
AiX Collect Pro | Exploratory Testing for Settings pages- AiX BFS Collect Pro | Fathima Rahna | 2025-08-14 | 2025-08-14 | 3.75 | 3.75 | Completed | 2025-08-14
AiX Collect Pro | Test case updation for AiX BFS Collect pro | Fathima Rahna | 2025-08-14 | 2025-08-14 | 3 | 3 | Completed | 2025-08-14
AiX Collect Pro | Exploring AiX Field Go APIs document | Fathima Rahna | 2025-08-18 | 2025-08-18 | 3 | 3 | Completed | 2025-08-18
Meeting | Standup (QA) | Fathima Rahna | 2025-08-18 | 2025-08-18 | 0.25 | 0.25 | Completed | 2025-08-18
AiX Field Go | API Testing -User and Attendance APIs- AiX Field Go | Fathima Rahna | 2025-08-18 | 2025-08-18 | 3 | 3 | Completed | 2025-08-18
AiX Field Go | Updating test cases for AiX Collect pro | Fathima Rahna | 2025-08-18 | 2025-08-18 | 1.75 | 1.75 | Completed | 2025-08-18
AiX Field Go | API Testing -User and Attendance APIs- AiX Field Go | Fathima Rahna | 2025-08-19 | 2025-08-19 | 3 | 3 | Completed | 2025-08-19
AiX Field Go | Exploring AiX Field Go APIs document | Fathima Rahna | 2025-08-19 | 2025-08-19 | 2 | 2 | Completed | 2025-08-19
AiX Field Go | API Testing -Dashboard and Tasks APIs- AiX Field Go | Fathima Rahna | 2025-08-19 | 2025-08-19 | 3 | 3 | Completed | 2025-08-19
AiX Field Go | Exploring AiX Field Go APIs document | Fathima Rahna | 2025-08-20 | 2025-08-20 | 1.25 | 1.25 | Completed | 2025-08-20
Meeting | Standup (QA) | Fathima Rahna | 2025-08-20 | 2025-08-20 | 0.25 | 0.25 | Completed | 2025-08-20
AiX Field Go | Creating Issue Report for API Testing | Fathima Rahna | 2025-08-20 | 2025-08-20 | 2.5 | 2.5 | Completed | 2025-08-20
AiX Field Go | API Testing -User and Attendance APIs- AiX Field Go | Fathima Rahna | 2025-08-20 | 2025-08-20 | 4 | 4 | Completed | 2025-08-20
AiX Field Go | Integration Checklist for Field Go and Collect pro | Fathima Rahna | 2025-08-21 | 2025-08-21 | 4 | 4 | Completed | 2025-08-21
Meeting | Standup (QA) | Fathima Rahna | 2025-08-21 | 2025-08-21 | 0.25 | 0.25 | Completed | 2025-08-21
AiX Field Go | Cleared doubts with the UI/UX designer and updated test cases for AiX Field Go | Fathima Rahna | 2025-08-21 | 2025-08-21 | 1.5 | 1.5 | Completed | 2025-08-21
AiX Field Go | API Testing- Tasks Page-AiX Field Go | Fathima Rahna | 2025-08-21 | 2025-08-21 | 2.25 | 2.25 | Completed | 2025-08-21
AiX Field Go | Integration Checklist for Field Go and Collect pro | Fathima Rahna | 2025-08-22 | 2025-08-22 | 4 | 4 | Completed | 2025-08-22
Meeting | Standup (QA) | Fathima Rahna | 2025-08-22 | 2025-08-22 | 0.25 | 0.25 | Completed | 2025-08-22
AiX Field Go | API testing for Blob, Auth, and Issue APIs, and creating issue reports | Fathima Rahna | 2025-08-22 | 2025-08-22 | 3.75 | 3.75 | Completed | 2025-08-22
AiX Field Go | API testing for User, Tasks, KYCand Collection APIs-AiX Field Go | Fathima Rahna | 2025-08-25 | 2025-08-25 | 4 | 4 | Completed | 2025-08-25
Meeting | Standup (QA) | Fathima Rahna | 2025-08-25 | 2025-08-25 | 0.25 | 0.25 | Completed | 2025-08-25
AiX Field Go | Bug Reporting in JIRA for Field Go APIs | Fathima Rahna | 2025-08-25 | 2025-08-25 | 3.75 | 3.75 | Completed | 2025-08-25
AiX Field Go | Regression testing for User, Dashboard, Attendance and Blob APIs- AiX Field Go | Fathima Rahna | 2025-08-28 | 2025-08-28 | 3.75 | 3.75 | Completed | 2025-08-28
Meeting | Standup (QA) | Fathima Rahna | 2025-08-28 | 2025-08-28 | 0.25 | 0.25 | Completed | 2025-08-28
AiX Field Go | Testcase execution for Login and Sign up- AiX FieldGo | Fathima Rahna | 2025-08-28 | 2025-08-28 | 4 | 4 | Completed | 2025-08-28
AiX Field Go | Testcase execution for Login and Sign up- AiX FieldGo | Fathima Rahna | 2025-08-29 | 2025-08-29 | 3.75 | 3.75 | Completed | 2025-08-29
Meeting | Standup (QA) | Fathima Rahna | 2025-08-29 | 2025-08-29 | 0.25 | 0.25 | Completed | 2025-08-29
AiX Field Go | Regression testing for Issue , Auth, Health, KYC and Tasks APIs- AiX Field Go | Fathima Rahna | 2025-08-29 | 2025-08-29 | 4 | 4 | Completed | 2025-08-29